## Sheet1
Epic | Story | Task | Sub-Task
1.Login Management | 1.Login with phone | 1.Verify mobile number and register user | 1.1.Get mobile number from user and validate it
1.2.Generate OTP,send to user this OTP then validate it,If validation true then register user
1.3. Insert record for this User in Login table with value custId,username(Mobile number),status
| 2.Login with Facebook | 1.Register with facebook to get clientId and secret | 1.Register with facebook to get clientId and secret
|  | 2. Create function & register user | 2.1 Create function which call facebook with username
2.2 Validate username
2.3 If validation true then insert record into login table with custid,username(facebook username),status
| 3. Login with google | 1.Register with google to get clientId and secret | 1.Register with google to get clientId and secret
|  | 2. Create function & register user | 2.1 Create function which call google with username
2.2 Validate username
2.3 If validation true then insert record into login table with custid,username(google username),status
| 4. Update user | 1. Update user by custId | 1.1 Update user details by custId in user table
|  | 2. Delete user by custId | 2.1 Update user status in login table as Deactivate
2. Product management | 1. List Product | 1. List all product | 1.1 When user come to home page then load all product irrespective any category,limited product will load
|  | 2. List product by category | 2.1 Get product by category which is given by user
| 2. Post product | 1. Post rent product | 1.1 Insert product details in Requested table with requestedType: RENT and productStatus: NEW
|  | 2.Post sell product | 2.1 Insert product details in Requested table with requestedType: SELL and productStatus: NEW
| 3. Insert user details if it is new user | 3. Insert user details if it is new user | 3.1 Check user details available or not
3.2 If user details not available and requestType:RENT then ask all details of user like full name,mobile number, adderess,id proof and insert all this in user table
3.3 If user details not available and requestType:SELL then ask basic details of user like fullname ,mobile number,adderess and insert all this in user table
3. Cart Management | 1.Manage cart details | 1. Add to cart | 1.1 When user veiwing product and want to add this product on his card then by clicking on "Add to cart" button he can do, after that we insert this product details in cart table by custId and productId
|  | 2. Display cart details | 2.1 When user login and click to cart then all his cart details display by custId
|  | 3. Remove product from cart | 3.1 If user remove product from cart then remove this entry from cart table as well
| 2. Manage wish cart (requested product) details | 1. Add to cart | 1.User can requested any product to make it available. Here we insert product details in RequestedProduct table
|  | 2. Display cart details | 2.1 When user login and click to wish cart then all his cart details display by custId
|  | 3. Remove product from cart | 3.1 If user remove product from wish cart then remove this entry from RequestedProduct table as well
4. Payment Management | 1. Generate invoice | 1. Create invoice excluding pick/drop charges | 1.1 when customer click on order button then based on product create invoice including product price,GST(if applicable),tax
|  | 2. Create invoice including pick/drop charges | 2.1 When customer choos pick/drop by company then 1st we calculate pick/drop charges based on distance from logistic-source-destination-logistic if it is for one way. If customer choose round trip then logistic-destination-source-logistic this also added. ex. for onw way ( logistic-source-destination-logistic) km * Rs. per KM. for round trip ( ( logistic-source-destination-logistic) km * Rs. per KM)*2
2.2 Create invoice by adding product price,GST,tax and pick/drop price
| 2. Integrate payment getway | 1. Integrate payment getway | 1. Integrate payment getway
|  | 2. proceed to pay | 2.1 Create method to process payment
| 3. Create final invoice | 3. Create final invoice | 3.1 Create final invoice after payment done
| 4. send sms | 4. send sms | 4.1 Integrate sms server
4.1 Create function to send sms
| 5. Send Email | 5. Send Email | 5.1 Integrate email server
5.2 Create function to send mail
5. Transportation Management | 1. Generate trasporation invoice | 1. Generate trasporation invoice | 1.1 When customer choose pick/drop by company and payment done then generate a invoice including owner (full name,mobile number,address) ,tenant(full name,mobile number,address) ,product full details with status NEW
|  | 2. Find nearest logistic | 2.1 Find nearest logistic based on distance from source to logistic
2.2 Map generated invoice to this nearest logistic . (Every logistic has portal where they can see all invoice which is generated for them so then can compelet that request. That portal has 4 tab New,IN-Progress,Completed.cancle.This newly generated invoice show in New tab).
| 2. Changes invoice status | 1. Changes invoice status | 1.1 Initially invoice status is New but when logistic member start working on it then this status change to In-Progress , so after that this invoice display in In-progress tab
1.2 When logistic member complete this request then this status change to complete , so after that this invoice display in complete tab
1.3 When order cancled by user then this status change to cancle_by_user , so after that this invoice display in cancle tab
3.4 When order cancled by logistic then this status change to cancle_by_logistic , so after that this invoice display in cancle tab
| 3. Check balance | 1. Check completed trip balance | 1.1 Logistic member can check his completed trip paymeny. This we calculated based on all trip which has complete status by logisticMemberId, we sum all amount then return this.
|  | 2. Check cancle trip balance | 2.1 If logistic member went to pick product and found its damage then he can cancle order by informing to Tenant. But Logistic member went to owner place that's why he must get some amount so this we calculate based on all trip which has cancle_by_logistic status by logisticMemberId, we sum all amount then return this
5. Admin Module | 1. Create user | 1. Create logistic user | 1.1 Create user with role "Logistic" including details like full name,mobile number, address , gadi details and paper, id proof, joining date
|  | 2. Create office staff | 2.1 Create user with role "Office_staff" including details like full name,mobile number, address, id proof,joining date
| 2. Create role | 1. Create role | 1. Create role
| 3. Remove user | 1. Remove user | 1.1 Change status of user in login table as Deactivate